## Sprint 3
Sprint 3 Task Completion Checklist
Task | Team Member | Completed On: | Estimate | Time To Complete
T24 | Kaelan | Moved to Sprint 4 | 1 | Moved to Sprint 4
T25 | Seb | day 6 | 3 | 2
T26 | Seb | day 6 | 3 | 3 | Summary of Sprint 3 Workload
T27 | Oliver | day 13 | 2 | 1 | Team Member | Total Hours
T28 | Eliot | day 6 | 1 | 1 | Kaelan | 6
T29 | Kaelan | day 14 | 3 | 3 | Seb | 11.5
T30 | Eliot | day 7 | 1 | 1 | J-Mari | 8
T31 | Seb | day 7 | 4 | 3 | Eliot | 6.5
T32 | Oliver | day 13 | 1 | 1 | William | 2
T33 | J-Mari | Moved to Sprint 4 | 3 | Moved to Sprint 4 | OJ | 8
T34 | J-Mari | day 14 | 3 | 1
T35 | Will | day 14 | 1 | 1
T36 | Oliver/Kaelan | day 6 | 4 | 2
T37 | Oliver | day 6 | 2 | 1
T38 | Oliver | day 6 | 2 | 1
T39 | Oliver | day 6 | 1 | 1
T40 | Eliot | day 6 | 3 | 3
T41 | Seb/Eliot | day 7 | 3 | 3
T42 | J-Mari | day 14 | 2 | 2
T43 | Will | day 14 | 1 | 1
| Total testing hours | 10
| Bugs Total | Bugs found description | date found | date resolved
| 6 | logo overwriting header links | 2016-10-11 | 2016-10-11
|  | footer links misalinged | 2016-10-11 | 2016-10-11
|  | Updated merge error in which test cases were invalid assertions. | 2016-09-27 | 2016-10-11
|  | Prefilling values on forms not working | 2016-09-20 | 2016-10-11
|  | Text overfilling on main body of the contacts page | 2016-10-12 | 2016-10-19
|  | Text boxes length are overfilling/too big | 2016-10-12 | 2016-10-12

## Sprint 4
Sprint 4 Task Completion Checklist
Task | Team Member | Completed On: | Estimate | Time To Complete
T24 | Kaelan, OJ | day 12 | 1 | 1
T44 | Seb | day 4 | 1 | 1 |  | Summary of Sprint 4 Workload
T45 | Kaelan | day 4 | 2 | 2.5 |  | Team Member | Total Hours
T46 | OJ | day 9 | 3 | 2 |  | Kaelan | 3
T47 | OJ | day 9 | 1 | 1 |  | Seb | 4
T48 | Seb | day 4 | 2 | 2.5 |  | J-Mari | 5
T49 | Seb | day 4 | 1 | 1 |  | Eliot | 3
T50 | Elliot | day 8 | 3 | 4 |  | William | 1
T51 | J-Mari | day 14 | 2 | 2 |  | OJ | 5
T52 | William | day 13 | 1 | 1
T33 | J-Mari | day 7 | 3 | 3
20
| Bugs Total | Bugs found description | date found | date resolved | Total testing hours
| 3 | Arrows missing on the homepage | 2016-10-19 | 2016-10-19 | 15
|  | Admin table overflow | 2016-10-19 | 2016-10-19
|  | Dynamically generated rules button appearing in the wrong place | 2016-10-21 | 2016-10-21