## Sprint 1
Sprint 1 Task Completion Checklist
Task | Team Member | Completed On: | Checklist | Time To Complete
T01 | Kaelan | Day 3
T02 | Kaelan | Day 11 |  |  | Summary of Sprint 1 Workload
T03 | William | Day 4 |  |  | Team Member | Total Hours
T04 | Seb/OJ | Day 9 |  | 2 | Kaelan | 7.5
T05 | Eliot | Day 11 |  |  | Sebastian | 6
T06 | Eliot/Kaelan | Day 12 |  |  | Oliver | 6
T07 | J-Mari | Day 14 |  |  | Eliot | 9.5
T09 | Kaelan | Day 12 |  |  | William | 4
T10 | Sebastian | Day 9 |  |  | J-Mari | 4
T11 | Oliver/Sebastian | Day 14 |  | 2
T12 | Oliver | Moved to Sprint 2
T13 | Eliot | Day 11 |  | 6
T14 | Eliot | Day 14 |  | 2
T15 | J-Mari | Day 14

## Sprint 2
Sprint 2 Task Completion Checklist
Task | Team Member | Completed On: | Checklist | Time To Complete
T12 | OJ |  |  | 2
T15 | J-Mari |  |  | 1
T16 | Kaelan |  | 1 | 1 | Summary of Sprint 2 Workload
T17 | J-Mari |  |  | 3 | Team Member | Total Hours
T18 | Seb |  | 2 | 2 | Kaelan | 5.5
T19 | Kaelan |  | 2 | 3 | Seb | 6
T20 | Seb |  | 1.5 | 4 | Jmari | 5.5
T21 | J-Mari & Eliot |  | 3 | 3 | Eliot | 3
T22 | OJ |  |  | 2 | William | 1
T23 | William |  |  | 1 | OJ | 4